## Open Audits
Audit Ref | Audit Title | Internal Audit Opinion | Month Reported to JIAC | Priority Of Agreed Action For Management | Number Of Agreed Actions | Completed Actions | Actions On Track | Actions Overdue | Actions In Exception
19/20.02 | Follow Up 19/20 Visit 1 | No Opinion Given | 2019-07-01 | High | 2 |  | 2
|  |  |  | Medium | 1 |  | 1
18/19.15 | Open Investigations and Crimes | Partial Assurance | 2019-05-01 | High | 2 |  | 2
|  |  |  | Medium | 3 |  | 1 |  | 2
18/19.14 | SharePoint Security | Reasonable Assurance | 2019-05-01 | High | 1 | 1
|  |  |  | Medium | 2 |  | 2
|  |  |  | Low | 3 | 2 | 1
18/19.13 | Follow Up 18/19 Visit 2 | No Opinion Given | 2019-03-01 | Medium | 5 |  |  | 1 | 4
|  |  |  | Low | 1 |  |  |  | 1
18/19.12 | Subject Access Requests | Partial Assurance | 2019-03-01 | High | 2 |  | 2
|  |  |  | Medium | 2 | 1 | 1
|  |  |  | Low | 3 | 3
18/19.11 | Transport: Hire and Pool Vehicles | Partial Assurance | 2019-03-01 | Medium | 5 | 3 |  |  | 2
|  |  |  | Low | 2 | 2
18/19.10 | Freedom of Information | Reasonable Assurance | 2018-11-01 | High | 1 |  | 1
|  |  |  | Medium | 2 | 1 |  |  | 1
|  |  |  | Low | 3 | 2 |  |  | 1
18/19.09 | Human Resource Management Sickness Absence including Medical Retirement | Reasonable Assurance | 2019-03-01 | Medium | 3 | 2 |  |  | 1
|  |  |  | Low | 2 | 1 |  |  | 1
18/19.08 | Resource Management: Overtime | Reasonable Assurance | 2018-11-01 | Medium | 3 | 2 |  |  | 1
|  |  |  | Low | 1 | 1
18/19.05 | Police and Crime Plan | Reasonable Assurance | 2018-11-01 | Medium | 2 | 1 |  |  | 1
|  |  |  | Low | 2 | 1 |  |  | 1
18/19.04 | Key Financial Controls | Reasonable Assurance | 2018-11-01 | Medium | 4 | 2 |  |  | 2
|  |  |  | Low | 3 | 1 |  |  | 2
18/19.01 | Transparency: Specified Information Order | Reasonable Assurance | 2018-07-01 | Medium | 2 | 1 |  |  | 1
|  |  |  | Low | 9 | 9
17/18.13 | Data Quality | Partial Assurance | 2018-03-01 | High | 1 | 1
|  |  |  | Medium | 3 | 2 |  |  | 1
|  |  |  | Low | 1 | 1
17/18.08 | General Data Protection Regulation (GDPR) Governance | No Opinion Given | 2018-03-01 | Suggestion Only | 16 | 6 |  |  | 10
17/18.06 | Integrated Offender Management | Partial Assurance | 2018-03-01 | High | 1 | 1
|  |  |  | Medium | 2 |  |  |  | 2

## Closed Audits
Audit Ref | Audit Title | Internal Audit Opinion | Month Reported to JIAC | Priority Of Agreed Action For Management | Number Of Agreed Actions | Completed Actions | Actions On Track | Actions Overdue | Actions In Exception
19/20.01 | Vetting | Substantial Assurance | 2019-07-01 | Low | 2 | 2
18/19.07 | Bail Management | Partial Assurance | 2018-11-01 | High | 2 | 2
|  |  |  | Medium | 6 | 6
18/19.06 | Crime Data Integrity Action Plan | Partial Assurance | 2018-11-01 | High | 2 | 2
|  |  |  | Medium | 2 | 2
|  |  |  | Low | 5 | 5
|  |  |  | Suggestion Only | 1 | 1
18/19.03 | Commissioning: North Yorkshire Justice Service and York Youth Offending Team | Substantial Assurance | 2018-07-01 | Suggestion Only | 5 | 5
18/19.02 | Follow Up 18/19 Visit 1 | No Opinion Given | 2018-07-01 | Medium | 1 | 1
17/18.15 | Chief Officers and Independent Custody Visitors’ Expenses | Reasonable Assurance | 2018-07-01 | Medium | 4 | 4
|  |  |  | Low | 1 | 1
17/18.11 | Procurement | Substantial Assurance | 2018-03-01 | Low | 1 | 1
|  |  |  | Suggestion Only | 1 | 1
17/18.10 | Automatic Number Plate Recognition (ANPR) | Reasonable Assurance | 2018-03-01 | Medium | 4 | 4
|  |  |  | Low | 2 | 2
|  |  |  | Suggestion Only | 2 | 2
17/18.09 | Key Financial Controls: Fixed Assets | Substantial Assurance | 2018-03-01 | Low | 1 | 1
|  |  |  | Suggestion Only | 3 | 3
17/18.07 | Follow Up 17/18 Visit 2 | No Opinion Given | 2018-03-01 | Medium | 1 | 1
17/18.05 | Exhibits: Seizure, Storage and Disposal of Controlled Drugs OFFICIAL SENSITIVE | Partial Assurance | 2017-12-01 | High | 2 | 2
|  |  |  | Low | 2 | 2
17/18.03 | Code of Practice - Victims of Crime | Reasonable Assurance | 2017-12-01 | Medium | 3 | 3
|  |  |  | Low | 3 | 3
17/18.02 | Human Resources: Recruitment | Partial Assurance | 2017-12-01 | High | 1 | 1
|  |  |  | Medium | 5 | 5
17/18.01 | Community Safety Partnership Funding | Reasonable Assurance | 2017-09-01 | High | 1 | 1
|  |  |  | Medium | 2 | 2
17/18.04 | Follow Up 17/18 Visit 1 | No Opinion Given | 2017-12-01 | Medium | 1 | 1

## Follow Up Visit 1 1920
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action For Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | Bail Management Audit Action (Medium): Further guidance and specific processes to be developed in relation to released under investigation to include monthly reviews by OiC and supervisor reviews. | Hughes, Mark | McConnell, Leanne | Further guidance and specific processes to be developed in relation to ‘released under investigation’ to include monthly reviews by OiC and supervisor reviews. | 2019-09-30 | 2019-09-30 |  | Open | Medium
2 | Bail Management Audit Action (High): All released under investigation cases will be reviewed to ensure that where no further action has been conducted that the suspect has been informed. | McConnell, Leanne | Hughes, Mark | Reiteration of original management action: All released under investigation cases will be reviewed to ensure that where no further action has been conducted that the suspect has been informed. | 2019-09-30 | 2019-09-30 |  | Open | High
3 | Bail Management Audit Action (High): All released under investigation cases will be reviewed to ensure that where the investigation has been concluded that the custody record has been updated and the PNC amended. | McConnell, Leanne | Hughes, Mark | Reiteration of original management action: All released under investigation cases will be reviewed to ensure that where the investigation has been concluded that the custody record has been updated and the PNC amended. | 2019-09-30 | 2019-09-30 |  | Open | High

## Open Investigations & Crimes
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | All crimes should be recorded within 24 hours. A 24-hour list is in place for all occurrences which have not been crimed which is monitored and reviewed by CROMU. | Davison, Fiona | Graham-Marlow, Dorrinda | Guidance will be developed in conjunction with the Head of Economic Crime relating to the recording of fraud occurrences. | 2019-05-31 | 2019-07-31 |  | Exception | Medium | Revisions awaiting approval of FCIR ahead of publication.
2 | Automatic chasers are sent out to officers who have not crimed an occurrence within 24 hours and a log of how many chasers were required is maintained. | Proctor, Mark |  | When fully resourced, weekly reviews of the 'chasers' report will be undertaken and those with multiple reminders will be escalated to their supervisor and subsequently their area inspector. | 2019-09-30 | 2019-09-30 |  | Open | Medium
3 | Crimes are reviewed regularly by supervisors and this is recorded on the System Log. Officers record sufficient and regular detail. | Proctor, Mark |  | Reports will be obtained from HR of all officers on long term sick or who have been redeployed or left the force in the last 18 months. Supervisors will be identified and requested to review and reallocate crimes associated with that officer. See Note 2 | 2019-09-30 | 2019-09-30 |  | Open | High
4 | Crimes are finalised by CMU. | Proctor, Mark |  | Once the Business as usual workload is under control. A list of credible options for addressing the backlog will be developed and assessed by the crime data integrity group. With final approval being provided by the deputy chief constable. | 2019-09-30 | 2019-09-30 |  | Open | High
5 | Re-opened crimes require re-finalisation by CMU in all instances | Proctor, Mark |  | It will be explored whether the status of reopened crimes can be changed to 'under investigation' on the Crime Management Software. This will then alert the OIC who will then be able to re-finalise the crime. | 2019-06-30 | 2019-07-31 |  | Exception | Medium | Awaiting SMT decision

## SharePoint Security
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | Guidance on the use and administration of SharePoint has been created and published on the intranet in the form of user guides. | Wood, Louise |  | Management will ensure that a training programme for all site owners and identified IAOs is established to provide appropriate training in infosec responsibilities relating to SharePoint. Attendance and completion of these courses should be monitored. | 2019-12-31 | 2019-12-31 |  | Open | Medium | Update from S Haider – this is Louise Wood’s action as the RACI Accountable person on the intranet project, this was an action of the intranet project that was not completed to my knowledge. TRANSFER action to L WOOD, update Nov JIAC
2 | Missing control We noted in discussion with management an absence of security design documents for the SharePoint implementation. | Martin, Philip | Jones, Richard | Establish formal security standards for SharePoint, to provide a best practice benchmark to site owners, both for administration purposes and to assist with annual auditing and ongoing security monitoring. Further detail in Notes1. | 2019-09-30 | 2019-09-30 |  | Open | Medium
3 | As part of the security implementation, the permission level full control has been modified as full control NYP, which prevents the creation of new sites. | Martin, Philip | Jones, Richard | Management will perform a full (and periodic) review of the permissions matrix to identify anomalies (including those identified during this audit), and investigation and remediation as required. | 2019-06-30 | 2019-06-30 | 2019-07-16 | Complete, evidence required | High | Completed monitoring taking place ,evidence of completion required
4 | An annual review of all sites is proposed to establish that they are still being used and are still required. | Adair, James | Haider, Susan | Management will ensure that the auditing of site proliferation is formally documented as an audit procedure. Management may also wish to consider the formal design of a SharePoint taxonomy. | 2019-06-30 | 2019-12-31 |  | Exception - time extension | Low | This will be assigned to the Records Compliance Manager once in post (1st August – James Adair), so I think I estimated this action could be completed by December 2019. ADD J Adair and extend to Dec19
5 | Security breaches from SharePoint sites have been documented within the IT Risk Register. | Martin, Philip | Jones, Richard | Management will ensure that all security incidents, including their remediation actions, are fully recorded within the incident management system. | 2019-05-31 | 2019-05-31 | 2019-07-16 | Complete, no evidence required | Low
6 | We noted that there is currently no practical means of identifying which SharePoint sites contain personal or sensitive data. Such sites may require particularly robust control over permissions and/or more frequent security auditing. | Wright, Chris |  | Management should consider adding to the list of sites a data item indicating the presence of data falling into the Top Secret, Secret and Official – Sensitive classifications, and reviewing the security of these sites centrally and/or more frequently. | 2019-09-30 | 2019-09-30 |  | Open | Low | Update from S Haider – reassigned to C Wright, action underway. TRANSFER action to C WRIGHT, update Nov JIAC

## Follow Up Visit 2 1819
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | HR Recruitment Action: A review of the VMF approval process is already underway and will consider: • Swifter approval of vacancies where the vacancies involve a straight replacement. • The approval of VMFs by the EPG on an exceptional basis or at the Finance approval stage by the Chief Finance Officer. • Agree the process for processing leavers to ensure that this linked to recruitment. |  |  | Agree the process for processing leavers to ensure that this linked to recruitment. | 2019-03-31 | 2019-06-30 |  | Exception | Low | HR unable to provide update due to T2020 associated consultations & redundancy processes.
2 | HR Recruitment Audit Action: Management will: • Implement a process by which a formal job card is created agreeing all the key dates including the marketing strategy to be applied. • Implement a more customer focussed environment whereby guidelines are provided alongside recruiter and hiring manager up-skilling. This would be supported by an overarching formally documented marketing strategy with tiered options which would ensure that the most effective form of advertising is utilised. This will be supported by the approach to a new advertising contract as this is due to re-tender. | Holmes, Rosemarie | Consett, Leanne | Update recruitment tracker to include details of the marketing strategy. Develop and implement an overarching marketing strategy with tiered options which would ensure that the most effective form of advertising is utilised. | 2019-04-30 | 2019-06-30 |  | Exception | Medium | HR unable to provide update due to T2020 associated consultations & redundancy processes.
3 | ANPR Audit Action: Staff will be reminded of the process to retain evidence of approval for all ANPR searches on data over 90 days, including those who have authority to approve searches. The force's ANPR documents will be updated to detail provisions for access control audits. Audits of access to ANPR data will be carried out by the ANPR Data, Access and Technical Manager. We will undertake a brief exercise to ensure that no one currently has access to the Cleartone system that shouldn’t. We will then carry out a fully comprehensive exercise to review which roles should have access to the national system once ANPR data is moved over (beginning of May). | Stone, Donald |  | ANPR documentation will be updated to reflect that ANPR Manager will no longer be carrying out audits, but that RAU will. A pilot ANPR review will be undertaken in quarter one with implications to be carried out by June 2019. | 2019-06-30 | 2019-09-30 |  | Exception | Medium
4 | Chief Officer & Independent Custody Visitor Expenses Audit Action: The senior officer who had been getting their claim authorised by their deputy will be reminded that this is not appropriate. When the new expenses system is introduced, the current pre-payroll checks of the all chief officer expenses by a member of the finance SMT will continue (see recommendation four below). The QA process for all the rest of the expenses will include all other claims over a de-minimus limit and between 10% and 20% of all other claims. ICV expenses will continue to be prechecked by the ICV Coordinator. The decision not to pre-authorise will be reviewed after a period of operation, taking into account particularly the number of claims rejected or amended after review | Palmer, Jane |  | The QA process will include all claims over a deminimus limit and between 10% and 20% of all other claims. ICV expenses to be pre-checked by ICV Co-ordinator. Review decision not to pre-authorise after a period of operation, accounting for rejects/amends. | 2019-04-30 | 2019-09-30 |  | Exception | Medium | Update from J Palmer 24/06/19: We have having problems vis-à-vis the supplier as regards implementation of the electronic expenses system. Since the system is not in place the relevant QA checks have also not been implemented. The Payroll Manager and I are working with the supplier to sort this issue
5 | Exhibits: Seizure, storage & disposal of controlled drugs Audit Action: The FEM has undertaken an investigation in order to locate the identified exhibits from our testing sample. The three ‘not controlled’ substances at York have been confirmed as destroyed and the Scarborough exhibit has been located. One exhibit remains outstanding and a referral has been made to Professional Standards for further investigation. Audits / reconciliations of drugs exhibits will be undertaken, as a minimum, on a quarterly basis by the FEM or nominated appropriate individual to ensure all drug exhibits can be accounted for. | Connolly, Emma |  | Dip sample audits will be conducted at the Exhibits store on a regular basis (for each category of property as a minimum monthly), as documented in the BAS Exhibits Audit Manual. | 2019-11-30 | 2019-06-30 |  | Exception | Medium | With regards to the audits, dip samples of property within the stores takes place on a monthly basis and these are documented and stored locally. However due to the T2020 recommendations, a number of my team were at risk of redundancy and we have lost the Exhibit manager post through this process, and although the audits are been undertaken they are not as scheduled as they should be. For that reason I would like to extend this action for review later in the year (Nov/Dec) due to the massive structural changes within the department to ensure we have robust audits regimes in place due to the change in management.
6 | Data Quality Audit Action: Other areas of the Home Office Counting Rules will be reviewed as part of the Force Crime and Incident Registrar's annual audit plan. Regular monitoring of crime recording will be undertaken by supervisors, this monitoring will be reviewed by the Information Management Team to inform their audit plan, identify areas of weakness and to take assurance where crimes are being recorded in accordance with National Crime Recording Standards and Home Office Counting Rules. Resource for this team is being considered as part of the T2020 review, after which the capacity to undertake audits will be better understood. | Ansbro, Tricia | Proctor, Mark | Other areas of the HO Counting Rules will be reviewed as part of the FCIR's annual audit plan. Regular monitoring of crime recording undertaken by supervisors- reviewed by the IMT to inform audit plan, identify areas of weakness and to take assurance | 2019-03-31 | 2019-10-31 |  | Exception | Medium | Update FCIR 09/07/19 . This action has not yet been completed. The newly appointment CMU Managers (crime recording Supervisors) will, when staffing allows, undertaken regular quality assurance checks on their teams work and the FCIR will have oversight. As a result of the T2020 review, there have been significant staff shortages in the team and the managers have been assisting to clear backlogs. This position will improve as recruitment has now taken place. However, new staff need to be fully trained, realistically it is unlikely that CMU Managers will be in a position to commence regular audit activity until October 2019. In the interim, the FCIR and her team continue to undertake regular audit and assurance activity. Any areas of concern are raised via Crime Data Integrity Improvement Group and feedback provided on an individual basis

## Subject Access Requests
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | A Data Protection – Subject Access Procedure is in place covering the subject access request process which is available on the staff intranet. | Ward, Katie | Haider, Susan | The Data Protection – Subject Access Procedure will be updated to include the internal review process and escalation process. | 2019-04-30 | 2019-04-30 | 2019-04-30 | Closed | Low
2 | Subject access request forms are available at all police stations, NYP and OPFCC websites. |  |  | The PFCC website will be updated to include a link to the subject access request form and e-form. | 2019-04-30 | 2019-04-30 | 2019-04-30 | Closed | Low
3 | As per ICO guidelines, subject access requests are acted on | Wintermeyer, Jane |  | Resource to undertake subject access requests needs to be reviewed in order to increase the compliance rate. An assessment of resources required as well as where responsibility for subject access requests will be undertaken. (ABV) | 2019-12-31 | 2019-12-31 |  | Open | High
4 | Complex or numerous requests may be able to extend the response period by an additional two months. Where the one month statutory period will not be met, the applicant will be informed to advise them of the delay. |  |  | Action at Finding 3 | 2019-12-31 | 2019-12-31 |  | Open | High
5 | On a regular basis the DPOs undertakes a sample test of subject access requests to make sure they have been processed appropriately, the redactions made are justified and the exemptions clearly stated. | Wintermeyer, Jane |  | In the absence of resource working with the DPO it is difficult to prioritise these reviews, therefore the issue of resourcing will be considered as per action three. | 2019-12-31 | 2019-12-31 |  | Open | Medium
6 | Should a SAR not be satisfactory resolved, the subject can request an independent review by the DPO |  |  | Both websites as well as the subject access request form will be updated to include reference to the internal review process | 2019-04-30 | 2019-04-30 | 2019-04-30 | Closed | Low
7 | Compliance statistics relating to subject access requests are reported to the Executive Board. | Wintermeyer, Jane |  | As per the FOI process, Subject Access Requests should be reported to the Executive Board on an exception basis to ensure that the Executive Board are fully aware of issues relating to compliance (or non-compliance) with legislation. | 2019-04-30 | 2019-04-30 | 2019-04-30 | Closed | Medium

## Transport_Hire & Pool Vehicles
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | Hire car bookings are made via the business administrative services intranet site. When individuals require a hire car, they must fill out a car hire booking form and confirm that this has been authorised by their line manager. Fuel cards are issued to individuals when they receive the hire car by business administrative services and these are returned upon completion of the hire. As part of the booking form, the requestor is required to select the type of vehicle they require, with the default being a small car (category B) as this is the lowest priced vehicle. Should a hire car cancellation be required then the individual fills in another booking form to notify business administrative services that they wish to cancel the booking. | Brigginshaw, Bob |  | Where staff appear to fail to cancel car hires this will be followed up with them and their line manager to identify reasons why. Appropriate action will be taken with the individual | 2019-03-31 | 2019-03-31 | 2019-03-31 | Closed | Medium
1 | Hire car bookings are made via the business administrative services intranet site. When individuals require a hire car, they must fill out a car hire booking form and confirm that this has been authorised by their line manager. Fuel cards are issued to individuals when they receive the hire car by business administrative services and these are returned upon completion of the hire. As part of the booking form, the requestor is required to select the type of vehicle they require, with the default being a small car (category B) as this is the lowest priced vehicle. Should a hire car cancellation be required then the individual fills in another booking form to notify business administrative services that they wish to cancel the booking. | Williams, Kate |  | A reminder will be issued to all business administrative staff that only class B vehicles should be booked unless there are significant operational reasons for other classes of vehicle being hired. | 2019-02-28 | 2019-06-30 | 2019-06-17 | Closed | Low
2 | Employees in the first instance are required to use a car from the force pool or operational bank as an alternative to using their own vehicle. Operational bank vehicles are those that did belong to departments but have now been pooled for greater efficiency. Force pool vehicles are booked via the TranMan system available on the force intranet. Any member of staff can access this and book a pool vehicle if free for a specified period. There is no limit on the booking of pool cars and there is no time limit to which pool cars can be booked. Operational bank vehicles are vehicles allocated to departments and / or stations for use. There is no overall system for accessing these vehicles as they are first come first served and generally available via keys being available on boards in departments. | Brigginshaw, Bob | Undefined | Regular reports of vehicle use will be prepared and reviewed to understand the demand for vehicles. The fleet list and MAUDS data will be reconciled to ensure that the information is consistent and that the utilisation reports are being used correctly. | 2019-03-31 | 2019-03-31 | 2019-03-31 | Closed | Medium
3 | If force pool or operational bank cars are not available then employees are entitled to use their own private vehicle for mileage. However, the use of own vehicle to undertake a journey is restricted to over 70 miles (round trip) then the mileage over 70 will attract a reduced mileage rate (based on current HMRC rates for fuel only). In these circumstances the Maximum journey that can be undertaken in your own vehicle will be extended to 200 miles (round trip). Individuals must also have the following in place and checked by line manager: a valid driving licence, full business insurance, and up-to-date vehicle tax and MOT | Doolan, Barbara | Palmer, Jane | A reminder to all staff will be issued that all mileage claims should be fully completed to include destinations travelled to and from including postcodes. | 2018-12-31 | 2019-09-30 |  | Exception | Medium
4 | The transport decision tree specifies that pool cars must be utilised before hire cars are booked for individuals. The current process is that when a hire car booking form is completed and sent to business administrative services, business administrative services will undertake a manual intervention and review whether there is availability of operational pool cars. | Brigginshaw, Bob |  | The TranMan system will be updated to only allow bookings of pool cars one month in advance | 2019-03-31 | 2019-03-31 |  | Closed | Low
5 | Hire car expenditure is monitored by the transport team who are provided with monthly reports from Enterprise Rent-a-Car identifying the amount that has been spent in the previous month and also year to date. Minibus and van hire expenditure is also monitored by the transport team. There is no specific individual or team responsible for the monitoring of expenditure relating to private mileage claims as these are included in staff costs for individual departments. The Head of Transport and Logistics reports this information to the Executive Team on a six monthly basis in order to give them oversight of the current spend in relation to transport | Doolan, Barbara | Palmer, Jane | Costs relating to employee mileage claims will be provided to departmental heads | 2019-05-31 | 2019-09-30 |  | Exception | Medium
6 | North Yorkshire Police (NYP) have in place a documented procedure in relation to use of vehicles. The procedure covers the use of all marked and unmarked vehicles owned, hired, leased or sponsored by NYP. It also covers the use of private vehicles or any other vehicle that is used by an NYP employee or volunteer in connection with any NYP business. The procedure is supported by the transport decision tree which outlines the options available to staff and officers when considering undertaking journeys. Staff and line managers are required to use the tree and make appropriate assessment relating to the appropriate option to take prior to making each business journey. | Flint, Richard |  | Include the transport decision tree as part of an enhanced Use of Vehicles Procedure. | 2019-03-31 | 2019-03-31 | 2019-03-31 | Closed | Medium

## Freedom of Information
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | FoI requests can be made through a number of channels including letter, email and social media. All requests for information are received by both the force and the Office of the Police and Crime Commissioner (OPCC). FoI requests are then passed over to the Civil Disclosure Unit (CDU). Once the requests are received they are logged by the Civil Disclosure Unit (and the Office for the Police and Crime Commissioner, where applicable) on a daily basis. | Wintermeyer, Jane | Ward, Katie | Roles and responsibilities of the OPCC and the Civil Disclosure Unit will be clearly defined, agreed and documented to avoid confusion and duplication. A meeting will be held between the OPCC and CDU to clarify this. | 2018-12-31 | 2019-09-30 |  | Exception | Medium | Update Katie Ward Police Lawyer (Civil Disclosure Unit ) (PLCDU) 15/02/19: Meeting held on the 21/01/19, PL Actively engaged with OPFCC discussing roles and responsibilities, this is part of the Enable therefore it is required to extend this to the 30 April 2019. Update Katie Ward 09/05/19: This is currently in the hands of Will and Simon in the OPFCC. I have asked Will to keep me updated in connection with this. Simon is new in post, and this will be fully resolved over next few months.
2 | When an FoI has been received and logged on the FoI spreadsheet, the legal officer scheduled to check the FoI log for that day starts the FoI requests off by contacting the relevant department for information. Once the information is received back it is saved in the specific FoI file. The legal officers then select which FoI requests to process and respond to it. This is done on a judgemental basis but prioritised i.e. given to either the oldest request or ones due that day. The request is then assigned to that legal officer in CDU. | Wintermeyer, Jane |  | Consideration will be given within CDU as to how FoI requests are allocated and for both setting off and responding to requests. Position will be initially reviewed early January 2019 with a further review taking place in June 2019 | 2019-06-30 | 2019-06-30 | 2019-06-28 | Closed | Low
3 | FoI requests are responded to within 20 days in line with the ICO guidance. Where the response period is exceeded there is a reason for this. | Wintermeyer, Jane |  | Resource to undertake FoI requests will be reviewed in order to increase the compliance rate. A risk based assessment will be undertaken to determine whether the cost of increased resource outweighs the risks involved once response received from HR. | 2019-12-31 | 2019-12-31 |  | Open | High
4 | If a requester is not happy with the response they receive to their FoI request they are able to submit an internal review. There is an internal review process in place which is documented within the FoI procedure. All internal reviews are recorded on a separate tab of the FoI log. There is also a tab to record all complaints made to the ICO. The dates received and due dates of 20 working days are recorded on the log. Each internal is allocated to someone independent of the person responding to the original request. This is usually someone senior; the Police Lawyer. | Ward, Katie |  | The Police Lawyer (CDU) will attend FoI decision making training to enable them to undertake the reviews. | 2019-04-30 | 2019-04-30 | 2018-11-15 | Closed | Low
5 | FoI performance statistics are presented as part of the Corporate Health Pack to the Executive Board. FoI is presented to the Police and Crime Panel on a periodic basis. Information Assurance Board have FoI as a standing item on the agenda and performance indicators in relation to statutory information requests. Action plans are put in place to address under performance. | Wintermeyer, Jane |  | FoI request compliance will be scrutinised internally. This will be through the Executive Board holding the Head of Collaborative Legal Services to account for the performance of the unit. | 2019-01-31 | 2019-06-30 | 2019-06-13 | Closed | Medium
6 | North Yorkshire Police and the Police and Crime Commissioner publish the information detailed in the ICO's definition document on their website. There is a review process in place to ensure the information is kept up to date. | Wintermeyer, Jane | Ward, Katie | A review will be undertaken on an annual / six monthly basis to ensure all up to date information has been published.The departments will then work with Corporate Communications to update any out of date information. | 2019-01-31 | 2019-09-30 |  | Exception | Low | Recruited a 0.5 FTE Legal Officer on a fixed term contract until March 2020. She will be assisting with FOIs but this will not be sufficient resource to significantly improve the compliance rates. We are yet to hear whether we will be able to obtain any further resources for the unit or whether there is any possibility of this fixed term post becoming permanent. Require time to see how the recruitment of the new 0.5 FTE Legal Officer affects the compliance rates and we are also carrying a further 0.5 FTE Civil Disclosure Assistant vacancy pending the outcome of the T2020 consultations. going to need a few months to see the effects of this and to report to the SIRO so review in September 2019

## HR Management_Sickness Absence
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | There are several procedures and guidance in place to manage sickness absence including: - Police Staff Capability Procedure Attendance; - Management Guidance; - Quick Reference Guide - Sickness Supervisor Quick Reference Guide – Sickness. | Holmes, Rosemarie | Mekins, Sarah | Guidelines will be updated to include action to be taken in the event of noncompliance with the guidelines.? What action? | 2019-01-31 | 2019-04-30 |  | Exception | Low | Recommendation 1; Guidelines will be updated to include action to be taken in the event of noncompliance with the guidelines. The delay in response to this recommendation is due to absence, reduced staffing and the work required by T2020, it is requested that this recommendation is extended until the end of April 2019.
2 | ll individuals must notify the Force as soon as possible of their absence from work, unless there are exceptional circumstances that prevent them from doing so. If an individual is feeling unwell, and needs to go home, they must speak to their line manager or, if not available, another appropriate line manager before leaving work. Reasons for absence are documented on the Origin system. | Holmes, Rosemarie | Mekins, Sarah | Individuals and line managers will be reminded of the importance of recording the sickness absence on the Origin system as soon as the absence commences. | 2018-11-30 | 2018-11-30 |  | Closed | Low
3 | If it becomes clear that the reason for absence is wholly or in part due to psychological issues a referral should be made to the occupational health department at the earliest opportunity. The line manager has the opportunity to submit a management referral to refer an individual for a medical examination to the occupational health department, in relevant circumstances, dependant on the time period involved. The HR representative may be consulted if necessary. All occupational health referrals and reports are kept on personal files. | Holmes, Rosemarie | Mekins, Sarah | Reminder will be issued to all line managers to ensure referrals to occupational health are made in line with the Attendance Management Guidelines. | 2018-11-30 | 2018-11-30 |  | Closed | Medium
4 | Upon return to work, a return to work meeting must is held between the individual and the line manager, and discussion details recorded on the Origin system. There is no set timeframe within the attendance management guidance as to when a return to work interview should take place. | Mekins, Sarah |  | Line mangers will be reminded of the importance of undertaking return to work interviews | 2018-11-30 | 2018-11-30 |  | Closed | Medium
5 | Once the IRMP/SMP have provided their report to HR and given an opinion as to whether then individual is permanently incapacitated/medically unfit, a report is prepared for the Chief Constable / Interim Chief Executive Officer in order that they can make a decision regarding retirement on the grounds of ill health. This includes information provided by the individual, information from local management and a recommendation from the Head of Human Resources and Training. | Holmes, Rosemarie | Mekins, Sarah | Decision makers will be reminded of the requirement to make a decision within 30 days of the final SMP and IRMP report being received. | 2018-11-30 | 2019-04-30 |  | Exception | Medium | Decision makers will be reminded of the requirement to make a decision within 30 days of the final SMP and IRMP report being received. The delay in response to this recommendation is due to absence, reduced staffing and the work required by T2020, it is requested that this recommendation is extended until the end of April 2019.

## Resource Management_Overtime
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action For Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | There is a policy in place that covers overtime and time off in Lieu and this is available to all force staff via the intranet. This policy covers both police officers and staff and includes sections for both. The policy is supplemented by the Police Regulations 2003 which set out the entitlements of police officers and the Police Staff Council (PSC) sets out the rates for police staff for working additional hours. | Consett, Leanne |  | Overtime and TOIL procedure to be updated with the correct review date. | 2018-12-31 | 2018-12-31 | 2019-04-29 | Closed | Low
2 | The force uses the Origin system that ensures that there is an automatic enforcement of the overtime rules as per the Police Regulations and the PSC Handbook. These rules are input into the Origin system by the Resource Management Unit and are applied to all claims processed. Claims must be made within a three month period of the actual overtime taking place. | Consett, Leanne |  | AMENDED ACTION: Remind staff and management of expectiations in relation to timeliness of clains via OLB and include procedural revisions and next consultated review in April 2020. | 2019-03-31 | 2020-04-30 |  | Exception | Medium | This action is not proportionate to the risk (from Leanne Consett will require some significant work as although the change is quite minor, consultation will be required with both Federation & Unison, whom I expect will not agree, and given our resources and other commitments I do not believe this is a priority, nor is it a statutory change.) - amend to reminder to staff via OLB and include in policy at next scheduled review in April 2020 when consultation will be undertaken for all changes. HR unable to provide update due to T2020 associated consultations & redundancy processes.
3 | The People Board receives monthly reports detailing the use of overtime globally throughout the organisation. They monitor the use of overtime within the organisation at a global level, whilst also identifying areas of concern with regards to overtime spend. | Consett, Leanne |  | Consider enhancing the info reported to People's Board to inc detail on types of overtime worked (planned & reactive across departments) and financial implications. See Note 1 for additional detail. | 2019-03-31 | 2019-06-30 | 2019-06-17 | Closed | Medium
4 | The force payroll supply a report to the finance team who produce various reports which includes overtime figures per command area. The information is reported to management through the leadership structure on a regular basis. | Consett, Leanne |  | Consideration should be given to the delegated approval levels for approving overtime claims and whether budget information should be provided to line mangers responsible for authorising overtime. | 2019-03-31 | 2019-06-30 |  | Closed | Medium

## Police & Crime Plan
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | There are two main meetings within the governance structure in which the PCC holds the Chief Constable to account for delivery of the Police and Crime Plan.These are the Public Accountability Meeting and the Executive Board. Performance information relating to the Police and Crime Plan is presented to the Public Accountability Meeting. Performance information in relation to the delivery plan is reported to the Executive Board that demonstrates the progress in implementing the outcomes contained within the Police and Crime Plan. | Earles, Maria | Blackburn, Caroline | Public Accountability Meetings will make explicit reference to the role in scrutinising Police and Crime Plan. Terms of Reference of the Public Accountability Meeting and Executive Board will be approved | 2018-11-30 | 2019-04-30 | 2019-03-26 | Closed | Low
2 | Partial missing control There are four key strategies, currently in development, to deliver the outcomes in the Police and Crime Plan. these are currently in the process of being agreed through the organisation’s governance structure. The four key strategies are: - People Strategy; - Digital Strategy; - Estates and Logistics Strategy; - Operational (Control) Strategy. Delivery of each of these strategies will be through service delivery plans, although these are not yet developed as the strategies must be developed firstly. | Earles, Maria | Blackburn, Caroline | Clear documented timelines for delivery of the key strategies and service plans will be developed. | 2018-09-30 | 2019-07-31 |  | Exception | Medium | New strategies not yet finalised (planning day 25/04/19), but a timeline has been agreed to develop these in line with service plans by 30/06 for COT sign-off by the end of July.
3 | For the financial year 2017/2018 a delivery plan was in place that captured the deliverables against the Police and Crime Plan. A delivery plan closure report was undertaken which identified key areas where progress had been made and also any outstanding deliverables which have been rolled into 2018 / 2019. There is no delivery plan in place for 2018 / 2019 as the strategies for delivering the Police and Crime Plan are still under development. | Earles, Maria | Blackburn, Caroline | Delivery of the Police and Crime Plan priorities in 2018 / 2019 will be clearly documented in developing strategies. | 2018-12-31 | 2019-07-31 |  | Exception | Low | New strategies not yet finalised (planning day 25/04/19), but a timeline has been agreed to develop these in line with service plans by 30/06 for COT sign-off by the end of July. .
4 | Information is requested by the PCC Policy and Scrutiny Officers from the Chief Officers Staff. Where information is required to support delivery of the Police and Crime Plan then this is collated by the Policy and Scrutiny Officers and presented to the Public Accountability Meeting. | Blackburn, Caroline | Blackburn, Caroline | Information being provided to the Public Accountability Meeting will make reference to the delivery of the four priorities included in the Police and Crime Plan. | 2018-12-31 | 2019-04-30 | 2019-05-08 | Closed | Medium

## Key Financial Controls
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | Suppliers initiate changes to supplier details through a number of ways: direct e-mail to the P2P team, direct email to other member of staff, letter received in the post and via invoice received. A supplier details form is completed by the supplier, returned to NYP and passed to the P2P Department for updating Oracle. | Johnson, Nicola |  | A detailed audit trail will be retained for all changes made within the Oracle system. | 2018-09-30 | 2019-03-19 |  | Closed | Medium
2 | When changes are made to supplier details within Oracle an audit trail is maintained detailing who has undertaken the change but not for what purpose. On a monthly basis, the P2P Manager undertakes a review of all supplier amendments and creations made in the Oracle system to ensure that they were created by authorised persons only. | Palmer, Jane |  | A supplier amendments and changes report will be run on a monthly basis and reviewed by the Head of Finance. | 2018-09-30 | 2019-03-19 |  | Closed | Medium
3 | Missing control The DRM Manual details who is responsible for the creation and amendment of supplier bank details. | Johnson, Nicola |  | A process map will be developed and approved that fully details the supplier creation and amendment process. | 2018-12-31 | 2019-07-31 |  | Exception | Low | Response 18768 Ref 3 Update Nicola Johnson P2P Manager and Jane Osborne Head Of Finance 07.02.19 low - ON HOLD Process map awaiting Transform 2020 outcomes in order to be in line with required process going forward On hold until 31.07.19
4 | Those staff who have responsibility for creating and amending supplier details have a limited role in the authorisation, requisition and purchase order approval process. | Palmer, Jane |  | Continue to allow approval but add report from PwC to show which PO requisition a particular user has authorised and show who authorised the resultant PO. Issue instructions where P2P Manager has authorised changes they will no longer approve PO | 2018-09-30 | 2019-07-31 |  | Exception | Medium | No update for Nov 18 JIAC re overdue completion - S Perkins to follow up and obtain update. Response 18767 Ref 4 Update Nicola Johnson P2P Manager and Jane Osborne Head Of Finance medium PARTIALLY CLOSED – P2P Manager no longer approves any purchase order where she has approved the requisition. No evidence for this. The suggested report has been scoped but is awaiting outcome of Transform 2020 review to assess requirement going forward. To be extended to 31.07.19
5 | All users have the ability to raise a requisition on the Oracle system, although not all users have the access rights to raise and approve purchase orders. Delegated limits are enforced on the Oracle system in line with the delegation scheme in place. | Palmer, Jane |  | DRM Manual to be reviewed to ensure that it reflects current practice. | 2018-12-31 | 2019-07-31 |  | Exception | Low | Response 18770 Ref 5 Update Nicola Johnson P2P Manager and Jane Osborne Head Of Finance 07.02.19 low REMAINS OPEN – NEW IMPLEMENTATION 31.07.19 - DRM has not been reviewed due to staffing changes
6 | The Oracle system automatically enforces a hierarchy within the purchasing process that means a requisition must be approved by an officer in the next hierarchical group, making it impossible to approve an order or requisition raised by the same individual. | Johnson, Nicola |  | Approver will be reviewed for the Customer Relationship Manager. | 2018-09-30 | 2018-09-30 | 2019-02-07 | Closed | Low
7 | Vacation rules are used in Oracle for an individual to set up a temporary delegation of their authority while away from the work place. The system then records the delegation in the approval chain, so reviews can be carried out. As an individual sets up this rule within their own account they are responsible for ensuring that the delegation is appropriate. | Johnson, Nicola |  | We will look into commissioning a report which details vacation rules and who has to set them up. This will be reviewed by the P2P Manager on a monthly basis. Any vacation rules set up by the P2P team will be approved by email in advance. | 2018-12-31 | 2019-07-31 |  | Exception | Medium | Response 18772 Ref 7 Update Nicola Johnson P2P Manager and Jane Osborne Head Of Finance 07.02.19 medium PARTIALLY CLOSED – No delegation is set up by P2P team without email authority. No evidence as there has not being an action. The suggested report has been scoped but is awaiting outcome of Transform 2020 review to assess requirement going forward. Extend to 31.07.19

## Transparency_SIO
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | Who we are & what we do Information about any arrangements that the PCC has to make use of the staff of the chief officer of police or a local authority. Publishing frequency To be published as soon as practicable after election, reviewed annually and updated when changes are made. Organisational chart and information on use of police force or local authority staff to be reviewed every six months rather than annually. | Naylor, Will | James-McGrath, Tina | Memorandum of Understanding will be subject to annual review. | 2018-08-31 | 2018-08-31 | 2018-10-25 | Closed | Low
2 | What we spend & how we spend it The budget for the office of the PCC, including: • all planned expenditure; • all anticipated revenue sources; and • the planned precept levels. Publishing frequency To be published before the start of each financial year. | Naylor, Will | James-McGrath, Tina | The budget for the relevant financial year will be uploaded prior to the commencement of that year within the budget and expenditure section. | 2019-03-31 | 2019-03-31 | 2018-10-18 | Closed | Low
3 | What we spend and how we spend it Details of each grant (including crime and disorder reduction grant) made by the PCC, including • the conditions (if any) attached to the grant; • the recipient of the grant; and • the purpose of the grant and the reasons why the body considered that the grant would secure, or contribute to securing, crime and disorder reduction in the body’s area, where appropriate. Publishing frequency To be published each month. | Naylor, Will | James-McGrath, Tina | Conditions attached to Community Safety Services Fund grants will be included, or if no conditions are applicable this will be clearly stated. | 2018-09-30 | 2018-09-30 | 2018-10-18 | Closed | Low
4 | What we spend and how we spend it Information as to any item of expenditure over £500 (other than crime and disorder reduction grants) by the PCC or the Chief Officer, including: • the recipient • the purpose of the expenditure; and • the reasons why the PCC or Chief Officer considered that VfM would be achieved (except contracts over £10,000. Publishing frequency To be published each month. | Naylor, Will | James-McGrath, Tina | Expenditure will be published on a monthly basis. | 2018-09-30 | 2018-09-30 | 2018-10-18 | Closed | Low
5 | What we spend and how we spend it Allowances and expenses: Details of the allowances and expenses that have been claimed or incurred by the PCC and Deputy PCC should publish a breakdown of their expenses including: • their name; • force area; • financial year; • month; • date; • claim reference numbers; • expense type (e.g. travel, accommodation); • short description; • details; • amount claimed; • amount reimbursed; • amount not reimbursed; • and the reason why a claim was not reimbursed. For travel and subsistence claims: date, place of origin, place of destination, category of journey, class of travel, mileage, length of hotel stay and category of hotel stay. Publishing frequency To be published each month. | Naylor, Will | James-McGrath, Tina | Expenses claims will detail length of hotel stay. | 2018-08-31 | 2018-08-31 | 2018-10-18 | Closed | Low
6 | What we spend and how we spend it Contracts & Tenders: • a list of contracts for £10,000 or less - to include the value of the contract, the identity of all parties to the contract and its purpose; • full copies of contracts over £10,000; and • copies of each invitation to tender which is issued by the PCC or the Chief Officer where the contract is to exceed £10,000. Publishing frequency Lists of contracts to be published quarterly. Contracts to be published as soon as practicable. | Naylor, Will | James-McGrath, Tina | For all contracts above £10,000, copies of the actual contract will be uploaded. | 2018-10-31 | 2019-05-31 |  | Exception | Medium | May JIAC: update from Tina James-McGrath: o The information required has now been received o This is being processed o This is due to be completed before the end of w/c 13.5.2019 and published accordingly
7 | What we spend and how we spend it Senior salaries: • the salary amounts above £58,200 including names (with the option to refuse name being published), job description and responsibilities in the office of PCC. Publishing frequency To be published as soon as practicable after election, reviewed annually and updated when changes are made. | Naylor, Will | James-McGrath, Tina | Roles and job descriptions for all those earning more than £58,200 will be added to the website. | 2018-09-30 | 2018-09-30 | 2018-10-24 | Closed | Low
8 | What our priorities are & how we are doing A copy of each collaboration agreement, or the fact that an agreement has been made and such other details about it as the PCC thinks appropriate. Publishing frequency No deadline specified - suggest within 2 weeks of collaboration agreement being made. | Naylor, Will | James-McGrath, Tina | All collaboration agreements will be uploaded in a timely manner. | 2018-10-31 | 2018-10-31 |  | Closed | Low
9 | Our policies & procedures The following policies and procedures to which the PCC and deputy must adhere to in the course of their role: code of conduct (if any), decision making (policy on), the procedure for the handling of complaints and the number of complaints against the PCC recorded by the Police and Crime Panel (as required by regulations). Publishing frequency To be published as soon as practicable, reviewed annually and updated when changes are made. Complaints to be published at the end of each financial year. | Naylor, Will | James-McGrath, Tina | Number of complaints received on an annual basis will be updated in a timely manner. | 2018-08-31 | 2018-08-31 |  | Closed | Low
10 | Our policies & procedures Record management information security policies, relating to records retention and destruction/archive policies. Data sharing policies (minimum standards to responding for requests for information). Publishing frequency To be published as soon as practicable, reviewed annually and updated when changes are made. | Naylor, Will | James-McGrath, Tina | All information management policies will be reviewed and uploaded to the website. | 2018-10-31 | 2018-10-31 |  | Closed | Medium
11 | Lists & registers: List of FOI requests received, and their responses (disclosure log). Publishing frequency To be published quarterly. | Naylor, Will | James-McGrath, Tina | The FOI disclosure log will be updated on a quarterly basis. | 2018-09-30 | 2018-09-30 | 2018-10-18 | Closed | Low

## Data Quality
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | Policies and supporting procedures are in place and provide direction and clarity on how the Force manage the recording of crimes. The documents are reviewed on a periodic basis and is available to staff. The following policies / procedures are in place to support data reporting: • Collection and Recording of Police Information Procedure; • Crime Recording and Occurrence Management Procedure; • Records Management Policy; • Data Quality Procedure; • Incident Management and Deployment Procedure; • National Crime Recording Standards Procedure; and • National Standard for Incident Recording Procedure. | Ansbro, Tricia | Fisher, Daniella | The up-to-date version of the National Crime Recording Standards procedure will be uploaded onto the intranet. | 2018-02-28 | 2018-02-28 | 2018-05-09 | Closed | Low
2 | The Force Crime and Incident Registrar develops an annual audit plan to commence in April each year. The audit plan is developed according to crime categories that present the highest risk to the public and / or the force and areas previously identified as requiring improvement. The audit plan is reviewed throughout the year at Ops Board meetings and Information Assurance Board (IAB) meetings and updated as and when there are changes in priority. If a specific issue is identified through scheduled activity or an ad-hoc audit is requested by the Chief Officer Team, then the audit schedule will be reviewed, amended and re-prioritised to accommodate the requirements. | Ansbro, Tricia | Fisher, Daniella | Other areas of the Home Office Counting Rules will be reviewed as part of the Force Crime and Incident Registrar's annual audit plan. Additional agreed action in notes. | 2018-07-31 | 2018-07-31 | 2018-05-09 | Closed | Medium
3 | When audits have been completed by the Force Crime and Incident Registrar, an Audit Summary Report is sent to the Responsible Managers which summarises the findings of the audit and lists recommendations. The new Crime Data Integrity (CDI) Improvement Group that is due to commence meeting in March 2018 and is chaired by the Deputy Chief Constable will discuss the annual audit plan, and findings from each audit at the CDI Improvement Group meetings. | Ansbro, Tricia | Undefined | The Information Management Team will consider introducing the improvements listed in notes below, alongside the agreed follow up actions to ensure ease of action tracking and accountability for recommendations. | 2018-07-31 | 2019-05-31 | 2019-07-09 | Closed | Medium
4 | The Designated Decision Maker (DDM) for the Force is the Service Improvement Manager. The DDM reviews crimes with outcomes 1a, 2a, 3a, 4 and 5, to ensure they have been recorded correctly and the correct outcome has been applied. There are some exceptions to these outcomes where the DDM does not need to review them (e.g. for alternative disposals, where initial offence charged was an assault, but the crime was closed as a lesser assault). | Ansbro, Tricia | Undefined | The FCIR will remind CMU when crimes need to be referred to the DDM. DIs will be reminded they must document what they have reviewed on crime records and the reasons for their decision | 2018-04-30 | 2018-04-30 | 2018-05-16 | Closed | High
5 | Outcomes are determined following the Home Office Counting Rules for Recorded Crime. There are 21 different outcomes for recorded crimes. There is a Data Quality Assurance Manual in place that provides guidance on what information needs to be recorded / evidenced for crimes under each outcome. | Ansbro, Tricia | Undefined | Officers will be reminded when to record the details listed in notes below on Niche. Community Resolution form / the caution read to offenders will be reviewed | 2018-07-31 | 2019-09-30 |  | Exception | Medium | 09/07/19 FCIR update - An audit of outcomes has been scheduled for August 2019. Schedule attached. Mar JIAC: Response 18465 Rec 5 – CDI improvement work continues and is a priority at present. As a result an outcomes audit has yet to be scheduled. This will be factored into the assurance schedule review for 2019/20. Please extend to the end of May 2019 Nov JIAC: Officers and staff have been reminded of their responsibilities in respect of outcomes, the effect of this has not yet been assessed as an outcomes audit has not been undertaken since this audit was. An audit will be scheduled once the DCI improvement work has been completed.

## GDPR
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | Business processes and data discovery | Haider, Susan | James-McGrath, Tina | A record will be maintained of: Location & origin of all personal data held in-house; How the data is stored; Classification of each piece of personal data; Arrangements are in place for it to be shared internally or with a third party; Clear data owner | 2018-05-25 | 2019-06-30 |  | Exception | Suggestion Only | CC:. Oct 18 - The work is complete, inevitably there will be further processing identified or new processing, these will be picked up by the DPO during DPIA process and by the IAOs as part of their annual assurance activities around information assets. PFCC: May2019 - Interim DPO in post due to post changes relating to T2020 - working to confirm updated position. Will be able to report by July JIAC. Feb 19 - The work is almost complete. Whilst focus is mostly on information assurance statements, there are still a few outstanding items left for some IAOs. IAOs have been advised the final deadline is end of March 2019. Oct 18 - Work is nearly complete and it is anticipated that it will be completed by end of October, beginning of November. Whilst attempts have been made to ensure that all processing has been captured, it is likely that further processing will be uncovered when further work is completed on DPIAs etc. Any further processing will also be picked up by the annual reviews.
1 | Business processes and data discovery | Ward, Katie | Haider, Susan | Organisations will document an action plan in relation to GDPR which will inc. gap analysis headings and the following key items: Actions to be undertaken; Responsibility; Timeframes; Progress indicators; and Monitoring activities to be undertaken | 2018-05-25 | 2018-05-25 | 2018-06-30 | Closed | Suggestion Only
2 | ICO Area: Third parties | Haider, Susan | James-McGrath, Tina | Ensure 3rd party data sharing agreements are GDPR compliant; Ensure data flow mapping undertaken for all 3rd parties; Ensure 3rd party contracts updated so data sharing & confidentiality agreements reflect GDPR standards; retrospective GDPR due diligence | 2018-05-25 | 2020-03-31 |  | Exception | Suggestion Only | 2.2: Ensure that for every third party a data flow mapping exercise is undertaken CC- completed Oct 2018. PFCC: May 19 - Interim DPO in post due to post changes relating to T2020 - working to confirm updated position. Will be able to report by July JIAC. 2.1, 2.3 & 2.4: CC - The dataflow arrangements are not yet confirmed. Once they are confirmed, we can start to address the gaps with information sharing agreements. We have the existing ISAs to review for compliance. Data Processing Contracts will also need to be put in place with all processors. This is dependent upon Civil Disclosure, DPO, ISO and SME resource. Oct 18 - Most data processors awaiting DPCs and information sharing arrangements awaiting ISAs have now been identified. Work is in progress to plug these gaps. The temporary Senior Support Officer is working through a lot of the DPCs. Civil Disclosure have the responsibility for the ISAs, progress with the ISAs is slow going due to resource within Civil Disclosure. PFCC - The dataflow arrangements are not yet confirmed. Once they are confirmed we can start to address the gaps with information sharing agreements. We have the existing ISAs to review for compliance. Data Processing Contracts will alos need to be put in place with all processers. This is dependent upon Civil Disclosure, PCC DPO, ISO, OPCC and SME resource. Oct 18 - Through the data mapping work, most DPCs and ISAs have been identified. Due to resourcing difficulties within the Civil Disclosure unit, progress with ISAs continues to be slow. The Data Protection Senior Officer working with the CC has been tasked to help progress much of the DPCs which have now been identified. The majority of PCC DPCs are ones that are joint with the CC and so therefore, this work can be progressed at the same time.
3 | ICO Area: Data ownership | Jones, Richard | Haider, Susan | Organisations will formalise arrangements for completion of mapping exercise to ensure all data and data owners have been captured. Once the data flows have been mapped, a review of data owners undertaken to ensure those identified are still appropriate | 2018-05-25 | 2019-06-30 |  | Exception | Suggestion Only | CC- completed Oct 2018. PFCC - Data mapping exercise almost complete. Additional work will need to be completed on ensuring there is the correct level of detail in certain areas. The information asset register and dataflow maps will be reviewed at least annally once complete. IAOs will be encourages to maintain the register on an ongoing basis if any chances, ahead of the annual review. Feb 19 - The work is almost complete. Whilst focus is mostly on information assurance statements, there are still a few outstanding items left for some IAOs. IAOs have been advised the final deadline is end of March 2019. May 19 - Interim DPO in post due to post changes relating to T2020 - working to confirm updated position. Will be able to report by July JIAC
4 | ICO Area: Data security system level controls | Jones, Richard | Undefined | Organisations to establish formalised plan to ensure access controls are appropriate & associated password policies are managed centrally. Long term, organisations will look at implementation of ISMS system in order to help protect info in line with GDPR | 2018-05-25 | 2019-12-31 |  | Exception | Suggestion Only | July 2019 - Following a review of corporate governance, the Digital Board has been disbanded. The recruitment of an ITSO (10.3 below) has been approved in the T2020 Business Case. Then recruited this action will be allocated to them as a priority. The ITSO (see point 10.3) will look at the implementation of ISMS system in order to help protect information in line with GDPR requirements once the post is filled. May 2019 - No update from R Jones DISG due to T2020 commitments. A Digital Board is in progress of being established, which will cover all digital matter across organisation, this will commence in September 2018. The Terms of Reference will include ensuring access controls to the systems are appropriate, will have an oversight on staff moving roles within the organisation; ensuring permissions to systems are pertinent to the role. A Digital Board is in progress of being established, which will cover all digital matter across organisation, this will commence in September 2018. The Terms of Reference will include ensuring access controls to the systems are appropriate, will have an oversight on staff moving roles within the organisation; ensuring permissions to systems are pertinent to the role. The ITSO (see point 10.3) will look at the implementation of ISMS system in order to help protect information in line with GDPR requirements once the post is filled.
5 | ICO Area: Data storage and retention | Haider, Susan | James-McGrath, Tina | Establish plan to review policies for storage & data disposal; Produce comprehensive, accurate & up to date record of data storage& retention locations, inc back-ups. Supported by relevant P&Ps. Carry out audits in accordance with data retention | 2018-05-25 | 2020-03-31 |  | Exception | Suggestion Only | 5.1: CC- Records Manager and Senior Support Officer to progresss this. May 19 - This work has been assigned to a temporary additional resource within the Data Protection Complaince Team - the resource is in place for 12 months and will tackle this piece of work in conjuction with Information Security team. Completion by March 2020. PFCC- Records Manager and Senior Support Offcer to progress this. Commissiong and Partnerships to continue to assist in relation to specific commissioning elements. May 19 - Interim DPO in post due to post changes relating to T2020 - working to confirm updated position. Will be able to report by July JIAC Feb 19 - The PFCC Retention Schedule is currently being updated and should be finalised in the next couple of weeks. Further work is being completed to ensure there are adequated processes within the OPFCC to ensure that the retention schedule is being followed 5.2: CC - DP procedure amended to reflect this. Next steps to meet with key business areas (inc O&D) to embed DPIAs from the very start of projects, new processing and procurement of new systems / processors May 19 - this procedure has been submitted to Policies and Procuedre for publishing. The DPO has also arranged to meet key business areas to introduce and train them on using this procedure and completing a DPIA. Comms and awareness will be published once the procudre is published PFCC - DP procedure amended to reflect this and communications have been circulated to members of staff. Work now needs to be completed with key business areas to help them embed DPIAs from the very start of projects, new processing and procurement of new systems / processors. Work continues on communication strategies to help individuals to understand the need to engage with the DPOs from the beginning so they can support the completion of the DPIAs. May 19 - Interim DPO in post due to post changes relating to T2020 - working to confirm updated position. Will be able to report by July JIAC Feb 19
6 | ICO Area: Awareness | Haider, Susan | James-McGrath, Tina | Ensure communication strategy in place with detailed timescales for updates on GDPR up to & beyond implementation25/05/18; Communicate role of DPO will be to all staff; Pending release of national training programme, check all staff trained by 25/05/18 | 2018-05-25 | 2018-05-25 | 2018-12-31 | Closed | Suggestion Only
7 | ICO Area: Data policy, roles and responsibilities | Haider, Susan | James-McGrath, Tina | The organisations document their plan to review and update the Data Protection Policy and other associated policies in line with GDPR requirements and ensure these are communicated with all relevant staff prior to 25th May 2018. See Notes below. | 2018-05-25 | 2019-06-30 |  | Exception | Suggestion Only | CC Complete. DPO in post 9/4/18. A business case supporting resources to fulfil the day business of data protection duties and to assist with achieving some of the backlog of work to achieve compliance with the legislation has been approved by PwC and is currently under consultation as part of the wider T2020 review. PFCC: May 19 - Interim DPO in post due to post changes relating to T2020 - working to confirm updated position. Will be able to report by July JIAC. Feb 2019 - Assessment completed on the demand of the PFCC DPO role, however, the matter is now subject to T2020 considerations and therefore it is not possible to progress this action at this time Work on going to assess demand of PCC DPO. There was also a need to wait for the Home Secretary's decision on fire governance. As the PCC's business case has now received approval, decisions will need to be made on the DPO function as a whole. A review of the support and resources for data protection is due to commence late summer and into autumn 2018, with a view to a business case being presented in readiness for implementation in April 2019. This, for the most part is in relation to the Chief Constable, however, the review will also take into account other areas such as Civil Disclosure who also support the PCC. .
8 | ICO Area: Individuals’ rights | Haider, Susan | James-McGrath, Tina | Ensure there is clear, concise, easy to understand privacy notices which are accessible to all data subjects in particular victims, witnesses, suspects and staff via the organisations’ website, intranet or leaflets to provide information (see notes below) | 2018-05-25 | 2019-06-30 |  | Closed | Suggestion Only
8 | ICO Area: Individuals’ rights | Haider, Susan | James-McGrath, Tina | The organisations will also review and consider the automation of the process of the systems used to ensure that data subject information can be deleted / rectified efficiently if requested by data subjects. | 2018-05-25 | 2020-03-31 |  | Exception | Suggestion Only | Mostly complete. Remaining outstanding below 8.3 The organisations will also review and consider the automation of the process of the systems used to ensure that data subject information can be deleted / rectified efficiently if requested by data subjects. CC extended to Mar2020 (Large piece of work udnerway with the IT workstream to: identify all systems then determine whether they are capable of meeting DP requirements. May be some system development required. Reliant upon DISG resource too). PFCC extended to Mar 2020. Currently unclear what impact there is on PCC side. However, there is a large piece of work underway with the IT workstream to: identify all systems then determine whether they are capable of meeting DP requirements. May be some system development required. Relianat upon DISG resource too. 8.2 PFCC - Some basic privacy notices have been uploaded onto the PCC website which includes a general privacy notice as well as ones for staff, recruitment, volunteers, webforms and social media, photos and images. There is still a need to provide some more detail within these privacy notces as well as a need to upload additional privacy notices in areas such as CCTV, Supporting Victims etc. Feb 19 - Work pended in this area to wait and determine what further changes were required as a result of taking over fire goverance. Work ongoing in this area. May 19 - Interim DPO in post due to post changes relating to T2020 - working to confirm updated position. Will be able to report by July JIAC
8 | ICO Area: Individuals’ rights | Haider, Susan | Undefined | Update any related policies for subject access requests under GDPR including: right to have info provided in commonly used & machine-readable format; 30-day limit on transmission of info; right to have a free provision of access to their information. | 2018-05-25 | 2018-05-25 | 2018-05-25 | Closed | Suggestion Only
8 | ICO Area: Individuals’ rights | Haider, Susan | James-McGrath, Tina | The organisations will also amend all staff contracts to include updated information for compliance with GDPR. | 2018-05-25 | 2018-05-25 | 2019-01-31 | Closed | Suggestion Only
8 | ICO Area: Individuals’ rights | Ward, Katie | Undefined | The organisations will put comprehensive plans in place with responsible owners and timescales to ensure that individual rights processes are in place. | 2018-05-25 | 2018-05-25 | 2018-05-25 | Closed | Suggestion Only
9 | ICO Area: Consent | Haider, Susan | James-McGrath, Tina | The organisations will ensure that actions in notes below are completed | 2018-05-25 | 2020-03-31 |  | Exception | Suggestion Only | CC: Once all points of processing based on consent are identified we will look at the method of obtaining consent, amend if necessary and review the privacy notices provided at time of consent. Will also introduce mechanism of recording the consent, to use when conducting consent audits. Oct 18 - Forms and processes that have been identified to collect information based on consent, have been amended to include references to consent and the individual's rights. There may be more that havent yet been identified, but these should be picked up when we come to look more closely at conducting consent audits. Update Jan 19 - by 31st March 19 we will have linked with Risk & Assurance to work alongside their audit schedule to pick up all consent audits reequired. By summer 19 the aim is to get the consent audits underway. May 19 - with the pressures and worklod of the DPO, it has not been possible to conduct consent audits where appropriate, this will be the focus of the Deputy DPO once in post PFCC Once all points of processing based on consent are identified we will look at the method of obtaining consent, amend if necessary and review the privacy notices provided at time of consent. Will also introduce mechanism of recording the consent, to use when conducting consent audits. Update Jan 19 - by 31st March 19 we will have linked with Risk & Assurance to work alongside their audit schedule to pick up all consent audits reequired. By summer 19 the aim is to get the consent audits underway May 19 - Interim DPO in post due to post changes relating to T2020 - working to confirm updated position. Will be able to report by July JIAC DISG - July 2019 - The new Digital Roadmap (subject to approval and funding) has included a project to implement appropriate software tools. Delivery by 31/12/2024
10 | ICO Area: Data Breach | Haider, Susan | James-McGrath, Tina | The organisations will document plans to undertake the actions detailed in notes below. | 2018-05-25 | 2020-03-31 |  | Exception | Suggestion Only | 10.1 - complete 25/05/18 10.2 - CC complete JAn 2019. PFCC - In progress - commissioned services have provided a form (based on the internal e-form) and have been provided with the 'security breach inbox' email address to report their breach within 24 hours. Regional procurement have issued a letter to all contractors with instructions on reporting breachhes to the data controller within 24 hours. Still work to do on this, need to identify all data processors first through IAO dataflow mapping. Then will contact all processors and other third parties with instructions on data breach reporting processes. Update Jan 19 - in all exising DPCs and ISAs we review and new arrangements we implement, we have included breach reporting procedure. In Spring of 2018, Regional Procurement wrote to all third parties we have contracts with, explaining new obligations under DPA18 and referenced the need to report breaches to appropriate DPOs and/or ISOs. This now complements the work already completed as per previous update. May 19 - Interim DPO in post due to post changes relating to T2020 - working to confirm updated position. Will be able to report by July JIAC 10.3 - The recruitment of an ITSO has been approved in the T2020 Business Case, and will commence shortly. Complete by 31/10/19.
11 | ICO Area: Law Enforcement Directive (LED) / Data Protection Bill | Haider, Susan | Undefined | The Force will put in place comprehensive action plans to address the activities listed in notes below | 2018-05-25 | 2023-03-31 |  | Exception | Suggestion Only | Only applicable to CC. 11.2 Large piece of work underway with the IT workstream to: identify all systems then determine whether they are capable of meeting DP requirements. May be some system development required. Reliant upon DISG resource too. Oct 18 - Deferred estimated completion date to 6th May 2023 as per the transition period stated in Schedule 20 of DPA18. Raised at IAB in October 2018, DPO to do some fact finding nationally to understand the parameters of this and to understand national system development. DPO to bring a further dicussion paper to IAB in January 2019. 11.1 Complete 11.3 The dataflow arrangements are not yet confirmed. Once they are confirmed, we can start to address the gaps with information sharing agreements. We have the existing ISAs to review for compliance. Data Processing Contracts will also need to be put in place with all processors. This is dependent upon Civil Disclosure, DPO, ISO and SME resource. 11.4 Complete

## Integrated Offender Management
Finding Ref | Control Tested | Responsible Officer 1 | Responsible Officer 2 | Agreed Action for Management | Baseline Due Date | Due Date | Completion Date | Status | Priority | Exception Rationale
1 | There is an effective strategic IOM partnership supporting local delivery to reduce the reoffending of the cohort: • IOM partnership strategy; • IOM multi-agency agreement; • Strategic and operational meetings are held to develop practice and assess performance; and • Cohort is agreed by multiple agencies. | Harder, Allan | Wynne, Fiona | Work with partners at a strategic level to understand the appetite for a continued IOM scheme. See further in Notes below. | 2018-06-30 | 2019-03-31 | 2019-05-02 | Closed | High
2 | The local IOM scheme has developed in line with national best practice, including the following: • Cohort reflects the offending profile of the force rather than purely SAC offenders; • Training given to staff is relevant to the cohort managed; • Co-location of IOM staff and co-management of cohort at an operational level; and • Clear links between IOM staff intelligence and neighbourhood policing. | Harder, Allan | Wynne, Fiona | Actions as Finding1 at a strategic level. Following strategic decision making, reinvigorate with or without partners (depending on appetite) at a local level including improving channels for sharing best practice and escalating issues to a strategic level | 2018-06-30 | 2019-07-31 |  | Exception | Medium | Trinity has three levels - agencies predominantly NYP/ Probation/CRP (?). Scored on matrix - if over 30 adopted into scheme, less returns to nominating agency. If meets threshold, approach offender to work with us to address multi-agency needs to stop offending. It is offenders choice, and decision shared with local teams if decline. Uplift from PFCC of three officers to develop link between IOM and local policing teams. Advert is out, recruitment to follow. Where offenders are not engaging and there is evidence that they are still criminally active, an intel package will be sent through to TTCG to ensure that offenders are targeted by local police teams, with a view to disruption tactics being adopted to prevent offending and/or investigate any fresh offences. The plan is for the Trinity Scheme to go live in January 2019. A strategy document and operational guidelines have both been produced but at this time remain in draft form, pending final agreement by the OPCC and the COT. I anticipate that the scheme will be endorsed before the end of December 2018, but I cannot confirm this for definite as I cannot speak for the COT and/or the OPCC. The scheme will start to roll out in January and will be reviewed at the 6 month and 12 month stage.
3 | IOM performance management is effective. | Harder, Allan | Wynne, Fiona | As part of the strategic work design a new performance framework and template which informs best practice and gives senior leaders / managers a clear assessment of the performance of the scheme. | 2018-06-30 | 2019-07-31 |  | Exception | Medium | Dependent on Ocuma - planning is complete, implementation ongoing, performace data not yet available