## Risk register - as at 1 Oct 19
|  |  | Risk Assessment pre control |  |  | Risk Assessment post action plan
Risk no. (hyper-linked to action plan) | Risk Owner (Function) | Headline Risk | Likelihood | Impact on objective | Risk Score | Action Plan Reviewed Date | Likelihood | Impact on objective | Post Action Plan Risk Score | Target Score | Risk Description
RC 1 | Chair of Pension Board / Scheme Manager | Failure to put appropriate governance arrangements in place and monitor risk | 2 | 3 | 6 | 2021-01-18 | 1 | 3 | 3 | N/A | Scheme Manager and Pension Board awareness of legal responsibilities.
RC 2 | Scheme Manager | Failure to interpret rules or legislation correctly | 3 | 3 | 9 | 2021-01-18 | 1 | 3 | 3 | N/A | Appropriate Pension Board Member training and appropriate knowledge of Pension Provider.
RC 3 | Scheme Manager | Conflicts of interest | 2 | 2 | 4 | 2021-01-18 | 1 | 2 | 2 | N/A | All Pension Board members to declare any conflicts.
Op1 | Scheme Manager | Member data incomplete or inaccurate | 3 | 4 | 12 | 2021-01-18 | 1 | 4 | 4 | 4 | Data management and monitoring requirements under SLA fully understood and deemed adequate.
Op2 | Scheme Manager | Administration process failure / maladministration | 3 | 4 | 12 | 2021-01-18 | 1 | 4 | 4 | N/A | Formal SLA in place with third party administrator and monitoring arrangements assessed as adequate.
Op3 | Scheme Manager / Pension Scheme Administrator | Inadequate, late or inaccurate communications | 2 | 4 | 8 | 2021-01-18 | 1 | 4 | 4 | N/A | Communication requirements fully understood and The Pensions Regulator’s recommendations applied.
Op4 | Scheme Manager / Pension Scheme Administrator | Operational disaster (fire/flood etc) | 2 | 3 | 6 | 2021-01-18 | 1 | 3 | 3 | N/A | Business continuity procedures in place.
Op5 | Scheme Manager / Pension Scheme Administrator | Increased Future Workload / Complexities Resulting From Legal Challenges | 5 | 5 | 25 | 2021-01-18 | 5 | 2 | 10 | N/A | All parties (the Authority, enableNY and the pension board) consider and appreciate the increased workload (and associated complexities) stemming from public sector remedy and 'Matthews' (second RDS Modified exercise). | Op5 is the new risk that's been introduced in response to the future workload/complexities of remedy/Matthews
Fi1 | Scheme Manager / Pension Scheme Administrator | Excessive charges by suppliers / additional liabilities on the operating budget | 3 | 2 | 6 | 2021-01-18 | 2 | 4 | 4 | N/A | Regular checks of transactions and charges against contract terms/ robust methodology used to forecast pension accounting data.
Fi2 | Scheme Manager | Fraud / Fraudulent behaviour | 2 | 4 | 8 | 2021-01-18 | 1 | 4 | 4 | N/A | Budget monitoring and appropriate payment processes including use of authorised signatories and data validation.
Fu1 | Scheme Manager | Employer failure to pay correct contributions into scheme | 2 | 4 | 8 | 2021-01-18 | 1 | 4 | 4 | N/A | Contribution deductions and payments – monthly reconciliation of schedule of payments due and amount paid across.

## RC1
Title | Failure to put appropriate governance arrangements in place and monitor risk
Description | Scheme Manager and Pension Board awareness of legal responsibilities. |  |  |  | Back to: | Risk register
Type of Risk | To ensure regulatory and compliance measures are in place
Risk No. | RC 1 | LPB Owner | Chair of Pension Board / Scheme Manager
Pre Control Measure Risk Assessment
Likelihood | 2
Impact on Objective | 3
Pre Control Measure score | 6 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Pension Board given up to date information on legal responsibilities
2 | Terms of reference in place and under review
3 | Procedures for assessing and managing risk
4 | Procedure to identify, assess and report breaches
5 | Suitable frequency of Pension Board meetings
Post Control Measure Risk Assessment
Likelihood | 1
Impact on Objective | 3
Post Control Measure Score | 3
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A18: See guidance on scoring likelihood (this score may not change)
Note on A19: See guidance on scoring impact (the most likely to change)

## RC2
Title | Failure to interpret rules or legislation correctly
Description | Appropriate Pension Board Member training and appropriate knowledge of Pension Provider. |  |  |  | Back to: | Risk register
Type of Risk | To ensure regulatory and compliance measures are in place
Risk No. | RC 2 | LPB Owner | Scheme Manager
Pre Control Measure Risk Assessment
Likelihood | 3
Impact on Objective | 3
Pre Control Measure score | 9 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Up to date and documented training log, showing completion of scheme-specific training and The Pensions Regulator’s educational material
2 | Technical advice and regular updates made available
3 | Ongoing process for acquiring relevant knowledge and understanding, with regular refreshers
4 | Training of new Pension Board Members
5 | Board receives monthly bulletins from LGA and attends appropriate training events
6 | Awareness and understanding of relevant documentation as per TPR Code of Practice 14 paras 42-46
7 | Board receives monthly bulletins from LGA and attends appropriate training events
8 | Pension Provider have specialist knowledge of the regulations and tax rules
Post Control Measure Risk Assessment
Likelihood | 1
Impact on Objective | 3
Post Control Measure Score | 3
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A21: See guidance on scoring likelihood (this score may not change)
Note on A22: See guidance on scoring impact (the most likely to change)

## RC3
Title | Conflicts of interest
Description | All Pension Board members to declare any conflicts. |  |  |  | Back to: | Risk register
Type of Risk | To ensure regulatory and compliance measures are in place
Risk No. | RC 3 | LPB Owner | Scheme Manager
Pre Control Measure Risk Assessment
Likelihood | 2
Impact on Objective | 2
Pre Control Measure score | 4 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Conflicts of interest policy in place and fully understood
2 | Request for interests to be declared at each meeting
Post Control Measure Risk Assessment
Likelihood | 1
Impact on Objective | 2
Post Control Measure Score | 2
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A15: See guidance on scoring likelihood (this score may not change)
Note on A16: See guidance on scoring impact (the most likely to change)

## Op1
Title | Member data incomplete or inaccurate
Description | Data management and monitoring requirements under SLA fully understood and deemed adequate. |  |  |  | Back to: | Risk register
Type of Risk | To ensure Operational tasks are recognised and performed
Risk No. | Op1 | LPB Owner | Scheme Manager
Pre Control Measure Risk Assessment
Likelihood | 3
Impact on Objective | 4
Pre Control Measure score | 12 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Monthly processes to monitor records and carry out reconciliation
2 | Monthly KPI reporting on data issues – provide summary at each PB meeting
3 | Data review arrangements in place including periodic address cleanse
4 | Process to enact a Data Improvement Plan and report breaches, if required
5 | Compliant GDPR Privacy notices issued by NYFRS and WYPF and available on relevant website
6 | Monthly data postings sent to Pension Provider
Post Control Measure Risk Assessment
Likelihood | 1 | Introduced monthly postings as a control measure, but it became apparent that they weren't fit for purpose, and so the 'likelihood' is shown as '2' as a result
Impact on Objective | 4
Post Control Measure Score | 4
Action No. | Action |  | By whom | Target Date
1 |  | Discussed with NYCC about refining the report to make it fit for purpose by providing more automated information (addresses, contr rates etc). NYCC provided test files during Jan 2020, and these were agreed and signed-off by DH on 27 Jan 2020. A work instruction has been created to bring cohesion to the postings process, and a look-up formula is now in place that compares FireWatch addresses to Payroll addresses. Mismatches are referred to CAO or Payroll to correct. As at 23 March 2020, the returns up to and including October 2019 have been submitted (this new process saw returns July - October formatted and uploaded to WYPF within 3 days). This process works well, although additional report(s) need creating for the final month (March) to accurately capture annualised rates of pay plus pensionable allowances. That said, DH will ask the LPB to agree lowering this risk's score because of the progress made. LPB agreed at the 20 April 2020 meeting to reduce the post-control score to '4' (by reducing the likelihood from 2 to 1). | DH | 2020-02-01
2
3
4
5
Target Score | 4
Date Reviewed by action plan owner
Note on A19: See guidance on scoring likelihood (this score may not change)
Note on A20: See guidance on scoring impact (the most likely to change)

## Op2
Title | Administration process failure / maladministration
Description | Formal SLA in place with third party administrator and monitoring arrangements assessed as adequate. |  |  |  | Back to: | Risk register
Type of Risk | To ensure Operational tasks are recognised and performed
Risk No. | Op2 | LPB Owner | Scheme Manager
Pre Control Measure Risk Assessment
Likelihood | 3
Impact on Objective | 4
Pre Control Measure score | 12 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Quarterly client meetings and monthly reports including KPIs
2 | Ongoing dialogue between Scheme Manager and third party administrator, including process improvement plans
3 | Clear identification of roles, authority levels, data security and data protection processes
4 | Audit reporting on both third party administrator and Scheme Manager’s processes
5 | Ability to commission independent assurance report, if required
6 | Authority levels and signatory lists clearly documented and up to date
7 | Robust internal controls in place including counter checks of all calculations performed by Pension Provider
8 | Single point of failure with Payroll support and Pensions Admin Manager. Ensure there is a deputy and / or duties are documented to allow for service continuity in the absence of current post holders
9 | Protection of data and assets from ‘cyber risks’: the loss, disruption or damage as a result of the failure of its information technology systems and processes
Post Control Measure Risk Assessment
Likelihood | 1
Impact on Objective | 4
Post Control Measure Score | 4
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A22: See guidance on scoring likelihood (this score may not change)
Note on A23: See guidance on scoring impact (the most likely to change)

## Op3
Title | Inadequate, late or inaccurate communications
Description | Communication requirements fully understood and The Pensions Regulator’s recommendations applied. |  |  |  | Back to: | Risk register
Type of Risk | To ensure Operational tasks are recognised and performed
Risk No. | Op3 | LPB Owner | Scheme Manager / Pension Scheme Administrator
Pre Control Measure Risk Assessment
Likelihood | 2
Impact on Objective | 4
Pre Control Measure score | 8 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Communications provided under SLA fully understood and deemed adequate for basic requirements
2 | Ad hoc communications provided by LGA Pensions Adviser monitored, fully understood and tailored as necessary
3 | Develop Communications Strategy and keep under review
4 | Annual Benefit Statements (ABS) provided to all active scheme members by 31 August each year
5 | ABS provided to all deferred members on an annual basis
6 | Annual check by Scheme Manager to ensure all members have received an ABS
7 | Business processes in place to ensure the relevant legal statements are issued to any staff who are contractually or automatically enrolled
8 | Business processes in place to ensure communications with members affected by pay banding changes take place
9 | Monitor national member website (when available) to check effectiveness: decide then whether to signpost members solely to that, or to WYPF site following proposed revisions to it
10 | Pensions tax communicated via Internal Bulletins
11 | Opting-out: ensure wording on form / guidance adequately explains the benefits given up
Post Control Measure Risk Assessment
Likelihood | 1
Impact on Objective | 4
Post Control Measure Score | 4
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A24: See guidance on scoring likelihood (this score may not change)
Note on A25: See guidance on scoring impact (the most likely to change)

## I7 (hidden)
Title | Operational disaster (fire/flood etc)
Description | Business continuity procedures in place.
Objective | To ensure regulatory and compliance measures are in place
Risk No. | I 7 | CMB Owner | Head of Risk Management
Pre Control Measure score | 6 | Action Plan Owner | GM Response and Resilience
ACTION PLAN
Control no. | Control Measure
1 | Watching brief - weather warnings system in place
2 | LRF contacts in place
3 | BC secton on severe weather being included in revised IA plan
4
5
6
7
8
9
Post Control Measure Risk Assessment
Likelihood | 1 | No change as risk tolerable
Impact on Objective | 4 | No change as risk tolerable
Interdependency | #REF!
Post Control Measure Score | #REF!
Date Reviewed by action plan owner |  |  | 02/08/2018 removed
Note on A18: See guidance on scoring likelihood (this score may not change)
Note on A19: See guidance on scoring impact (the most likely to change)

## Op4
Title | Operational disaster (fire/flood etc)
Description | Business continuity procedures in place. |  |  |  | Back to: | Risk register
Type of Risk | To ensure Operational tasks are recognised and performed
Risk No. | Op4 | LPB Owner | Scheme Manager / Pension Scheme Administrator
Pre Control Measure Risk Assessment
Likelihood | 2
Impact on Objective | 3
Pre Control Measure score | 6 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Third party scheme administrator Disaster Recovery Plan up to date and appropriate
2 | Scheme Manager Disaster Recovery Plan up to date and appropriate
3 | Contracts and other essential documents recorded on a central database
4 | All pension and HR records are electronically stored and regularly backed-up
5 | For the duration of the COVID-19 pandemic, assurances regularly requested/received from WYPF regarding the measures they are taking to ensure core services are still being carried out, along with following national guidance (from LGA and the Pensions Regulator)
Post Control Measure Risk Assessment
Likelihood | 1
Impact on Objective | 3
Post Control Measure Score | 3
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A18: See guidance on scoring likelihood (this score may not change)
Note on A19: See guidance on scoring impact (the most likely to change)

## Op5
Title | Increased Future Workload / Complexities Resulting From Legal Challenges
Description | All parties (the Authority, enableNY and the pension board) consider and appreciate the increased workload (and associated complexities) stemming from public sector remedy and 'Matthews' (second RDS Modified exercise). |  |  |  | Back to: | Risk register
Type of Risk | To ensure data collation (including the identification of affected employees, and former employees) and adequate levels, frequency and mediums of communications are recognised and performed
Risk No. | Op5 | LPB Owner | Scheme Manager / Pension Scheme Administrator
Pre Control Measure Risk Assessment
Likelihood | 5 | Based on the 'Guidance' tab, this rating must be a '5' as Remedy and Matthews are definitely going to happen
Impact on Objective | 5 | Based on the 'Guidance' tab, the Board felt that this rating should also be a '5', both in terms of financial and knowledge impact: it is increasingly likely that immediate retirements will need to be processed on 'immediate detriment' terms in line with the Home Office 'guide' dated August 2020, and once remedy itself is formalised, there will need to be knowledge on the process over a good many years, especially as the Government have now confirmed 'Deferred Choice Underpin' as being the preferred member-election process
Pre Control Measure score | 25 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Requirement for strategic member of enableNY to attend pension board meetings to be informed of the latest developments from either remedy / Matthews
2 | Assurance that sufficient resource is available to meet the increased workload that is expected. This is difficult currently due to no tangible detail / guidance being available on either Remedy or Matthews to date, however, discussion with LGA indicates (the response to the Remedy consultation is expected Jan/Feb 2021 which may give a steer on next steps, whilst anything further on Matthews, and which people may be in scope, is unknown). Members of enableNY management team to attend strategic meetings to ensure they are fully versed on developments and can plan resources appropriately
3 | Assurance that sufficient experience and knowledge is available within the pensions function to meet the complexities of implementing remedy and Matthews
4 | Robust project plans created and agreed for both major exercises, ensuring all parties involved in the data gathering (Firewatch, Payroll, Pensions Manager/Administrator, communications lead) are clear on their responsibilities and timescales
5 | Creation of a communications strategy, to ensure all pension scheme members are appropriately informed at all times, and given appropriate guidance to help them exercise their choices. The comms strategy will incorporate the wording/forms produced by LGA (when available) alongside other direct forms of communications (Teams webinars) tailored, where possible, to tranches of members with similar circumstances. This could also include input from pension board members during the project / communication stages (possibly to cascade info to Group/Station Managers during the comms exercise)
Post Control Measure Risk Assessment
Likelihood | 5
Impact on Objective | 2
Post Control Measure Score | 10 | RAG ratings of amber require scrutiny from the pensions function head. It is believed that Claire Lister will remain as the pensions function head.
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A19: See guidance on scoring likelihood (this score may not change)
Note on A20: See guidance on scoring impact (the most likely to change)

## Fi1
Title | Excessive charges by suppliers / additional liabilities on the operating budget
Description | Regular checks of transactions and charges against contract terms/ robust methodology used to forecast pension accounting data. |  |  |  | Back to: | Risk register
Type of Risk | To ensure matters relating to Financial efficiencies are recognised and addressed
Risk No. | Fi1 | LPB Owner | Scheme Manager / Pension Scheme Administrator
Pre Control Measure Risk Assessment
Likelihood | 3
Impact on Objective | 2
Pre Control Measure score | 6 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Annual review of scheme budget, quarterly review of cost incurred against budget
2 | Periodic review of suppliers
3 | Processes in place to ensure robustness of method to forecast and calculate pension accounting data. Liaise with third party administrator when making forecasting assumptions
Post Control Measure Risk Assessment
Likelihood | 2
Impact on Objective | 2
Post Control Measure Score | 4
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A16: See guidance on scoring likelihood (this score may not change)
Note on A17: See guidance on scoring impact (the most likely to change)

## Fi2
Title | Fraud / Fraudulent behaviour
Description | Budget monitoring and appropriate payment processes including use of authorised signatories and data validation. |  |  |  | Back to: | Risk register
Type of Risk | To ensure matters relating to Financial efficiencies are recognised and addressed
Risk No. | Fi2 | LPB Owner | Scheme Manager
Pre Control Measure Risk Assessment
Likelihood | 2
Impact on Objective | 4
Pre Control Measure score | 8 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Monitor incoming and outgoing scheme funds and membership movements against scheme forecasts – reconcile actual transactions against forecasts
2 | Authorisation of transactions in accordance with audit requirements and carried out by authorised signatories only
3 | Robust data validation processes in place by third party administrator and Scheme Manager to ensure all transactions authentic
4 | Pension Provider staff have documented processes and both internal and external audit procedures
5 | Only pension forms and emails from authorised signatories accepted by Pension Provider
6 | Audit reporting on both third party administrator and Scheme Manager’s processes
Post Control Measure Risk Assessment
Likelihood | 1
Impact on Objective | 4
Post Control Measure Score | 4
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A19: See guidance on scoring likelihood (this score may not change)
Note on A20: See guidance on scoring impact (the most likely to change)

## Fu1
Title | Employer failure to pay correct contributions into scheme
Description | Contribution deductions and payments – monthly reconciliation of schedule of payments due and amount paid across. |  |  |  | Back to: | Risk register
Type of Risk | To ensure the Pension Account receives the correct monies in a timely manner
Risk No. | Fu1 | LPB Owner | Scheme Manager
Pre Control Measure Risk Assessment
Likelihood | 2
Impact on Objective | 4
Pre Control Measure score | 8 | Action Plan Owner | Head of Function for Pensions
ACTION PLAN
Control no. | Control Measure |  | Reviewed By | Review Date
1 | Processes in place to comply with regulatory requirements on contribution rates and pensionable pay definitions
2 | Suitable reporting and reconciliation processes in place ahead of payment including checks on changes in contract and transition to 2015 Scheme
Post Control Measure Risk Assessment
Likelihood | 1
Impact on Objective | 4
Post Control Measure Score | 4
Action No. | Action |  | By whom | Target Date
1
2
3
4
5
Target Score | N/A
Date Reviewed by action plan owner
Note on A15: See guidance on scoring likelihood (this score may not change)
Note on A16: See guidance on scoring impact (the most likely to change)

## Guidance
RISK SCORING GUIDANCE & TOLERANCE
Type of Risk
Each risk must be aligned to one of the following objectives and is numbered to include the relevant code.
RC = | To ensure regulatory and compliance measures are in place
Op = | To ensure Operational tasks are recognised and performed
Fi = | To ensure matters relating to Financial efficiencies are recognised and addressed
Fu = | To ensure the Pension Account receives the correct monies in a timely manner
Impact
The descriptors below are for illustration only. The score should be determined using judgement and knowledge of the type of risk impacted by the risk.
Likelihood
Likelihood should be scored using either the description or % chance
Score | Likelihood | Descriptor | % chance
5 | Very likely | At least once in the next 12 months | 80-100%
4 | Likely | Once every 1 to 2 years | 60-79%
3 | Probable | Once every 2 to 5 years | 40-59%
2 | Very unlikely | Once every 5 to 10 years | 20-39%
1 | Remote | Less than once every 10 years | 0-19%
RAG ratings of green require no action
RAG ratings of amber require scrutiny from the pensions function head
RAG ratings of red require scrutiny from the pensions board members
A 5 x 5 risk matrix covering Probability and Impact is used when assessing the level of risk.
The risk 'score' is identified by considering the probability of the event occurring, and the impact of the risk, should it arise.
A numeric value is applied to each of the selections for probability and impact, and these are referenced in the risk matrix to give a 'RAG' rated risk score.