## Slide 1: NYP National Child Protection Inspection (NCPI) Journey of Improvement Public Accountability Meeting Chief Constable Lisa Winward 3rd May 2023

## Slide 2: NCPI Improvement Timeline
Nov 2021 – NCP Inspection undertaken - followed by ‘hot’ verbal de-brief
Draft Action Plan formulated
‘GOLD’ oversight established
29th March 2022 – Formal NCPI report published
Action plan developed further
Dec 2022 – NCPI re-inspection – followed by ‘hot’ debrief
Intensified activity on areas for improvement
3rd May 2023 – formal report released by HMICFRS

## Slide 3: HMICFRS Next Steps
“North Yorkshire Police still needs to improve some areas of its work to provide consistently better outcomes for children. There has been some progress, particularly in the way the force has trained its workforce to identify children’s vulnerability and make good safeguarding referrals. Staff in the force control room have also made improvements so they are better at identifying risk and providing the right level of response to help vulnerable children.
Despite progress against some of our recommendations, the force has yet to make all the progress necessary to complete its action plan.”
This links to recommendations and improvements that are also being addressed in the wider PEEL inspection.

## Slide 4: NCPI Improvement Journey
Timeline for completion of key continuing improvement work
Rec 3 (Missing Children)
Rec 6 (Investigation Standards)
Rec 7 (CSE Awareness)
Rec 9 (Management of Offenders)
Context of wider organisational re-design and response to PEEL Inspection
Re-focusing of assurance capability to test delivery

## Slide 5: NCPI Improvement Journey
Re-inspection Dec 22 - some progress identified, insufficient improvement in other areas
Notable improvements in VOC (Voice of the Child) awareness and Public Protection Notice submissions-these safeguarding referrals have substantially increased but are not inappropriate or un-necessary and offer confidence in the officers training we have undertaken.
Improved relationship with statutory partners, especially regarding CSE
All actions will be implemented by October 2023 - enhanced testing and assurance will be undertaken to ensure practice is embedded.

## Slide 6: Approved Uplifted Resources (additional £2.9m to the existing budget)
Phase 1 Uplift – approved Feb 2023 – 21 posts
Cost c.£1.2m
1 x Inspector – MAPPA/IOM
1 x Sergeant – IOM
18 x PC – VAT (5)
        Child Exploitation (6)
        Missing Children (2)
        Sex Offender Mgr (2)
        Polygraph (1)
        IOM (2)
Phase 2 Uplift – approved April 2023 – 28 posts (17 PO / 11 Police staff)
Cost c.£1.29m
1 x DCI Governance
3 x Sergeant - Adult MASH
13 x Constables – Adult MASH (2)
        Adult Exploitation (2)
        Missing Adult (2)
        OMU DMI (1)
        Online Child Abuse Team (4)
1 x SO1 – DVPO Co-Ordinator
1 x Sc5 – MARAC Co-Ordinator
8 x Sc4-5 – Op Encompass
      OMU Research and Intel Officer
      VISOR Admin
      DA Research and Report Writer
      VAT Research and Report Writer

## Slide 7: NCPI AFIs From Initial Inspection
10 recommendations were provided by HMICFRS as AFIs (one has been remitted to the Custody Inspection).
Rec 1: Review processes in Force Control Room | Rec 6: Improve child protection investigations
Rec 2: Obtain voice of the child | Rec 7: Improve CSE understanding
Rec 3: Improve missing from home arrangements | Rec 8: Improve use of police protection powers
Rec 4: Work more closely with partners | Rec 9: Improve management of registered sex offenders
Rec 5: Review referral processes | Rec 10: Review detention of children management (remitted to another review).

## Slide 8: Rec 1: Review processes in Force Control Room
Pre Dec 22
Training provided to FCR staff around Missing From Home (MFH) deployment.
Power hour inputs on Child Protection topics.
Simplification of FCR question scripts.
MFH deployment procedures amended.
MFH policy reviewed
Trigger plans created for most vulnerable children to assist in risk assessment process with FCR staff shown what they contain and how to locate them.

## Slide 9: Rec 1: Review processes in Force Control Room continued…..
Dec 22 –now
Power Hours continuing throughout the year for call handlers, despatchers and deployment managers on identified topics where a need for upskilling is identified.
May 2023 –Digital Forensics Input.
June 2023- Looking Beyond the Obvious-Vulnerability –covering adult and child vulnerability scenarios .
July/August 2023 –Identifying Childhood Neglect.

## Slide 10: Rec 2: Obtain voice of the child Pre Dec 2022
Significant progress in this area since initial inspection.
Voice of Child (VOC) inputs to staff using a Domestic Abuse scenario/video to show how children can be witness to incidents and need to be spoken to and heard.
AWARE mnemonic included on various templates and documentation, such as Public Protection Notices. This has helped officers know what to observe and record in relation to children’s presentation at an incident.
Bespoke Keeping Children Safe site on intranet for officers up to date guidance
VOC & AWARE embedded into MFH return forms.

## Slide 11: Rec 2 Obtain Voice of the Child (VOC) cont’d…….
Dec 22 – now
Bespoke Voice of the Child video made for custody staff training and rolled out on all their development days covering what it is like through the eyes of a child entering custody
VOC 121 Refresh- video & training pack – this is a refresher to keep Voice of the Child alive and at the forefront- video shows an officer communicating with a child after a missing episode and the use of the AWARE on the return form –May 2023

## Slide 12: Rec 3: Improve missing from home arrangements
Pre-Dec 22
Training for response officers delivered in December 2022 on Exploitation and Missing Children.
Force Control Room power hour training.
Dec 22 - now
Cultural shift – perceptions of risk
Training for all Critical Incident Inspectors and Force Incident Managers - May 2023.
New IT enhancements to oversee missing management Sept 23.
Significant training front line training programme. Summer 23
Resource uplift into centralised Missing Team – 6PCs.

## Slide 13: Rec 4: Work more closely with partners
Pre Dec 22
Strong partnership arrangements with statutory agencies partners recognised by inspection team.
Increased Police Protection Notices submitted for triage with partners.
Enhanced escalation processes with partners
Dec 22 – now
Ongoing work to align processes in both Local Authorities in the MASH and MACE.

## Slide 14: Rec 5: Review referral processes
Pre - Dec 22
An area that was highlighted as having made significant progress since initial inspection.
Close working relationship has developed with Local Authority Multi-Agency Safeguarding Hub.
Referral processes changed.
PPN submission numbers greatly increased but appropriate.
Ongoing work with both Local Authorities to enhance the alignment between Police and Local Authorities to achieve consistency across the County.
Public Protection Notices
(referrals numbers) – 63% increase
2020 -2021 11909
2021 - 2022 - 13981
2022 - 2023 - 18910

## Slide 15: Rec 5: Review referral processes
Dec - Now
Continue with developing the pro forma used by officers for the content of their safeguarding referrals
Bespoke pro forma used by OMU
Bespoke pro forma used by OCAT
Process for quality and assurance of safeguarding referrals developed
Bitesize online learning in development to enhance officer’s knowledge of the journey of the referral and partnership working in the MAST/MASH

## Slide 16: Rec 6: Improve child protection investigations
Pre Dec 22
Crime allocation procedure was implemented that clarified roles and responsibilities.
Increased Specialist Child Abuse Investigation Development Programme trained officers and portfolio completion ensuring there are sufficient accredited Detectives.
As of 26/04/23 93 trained in SCAIDP. 30 portfolios signed off.
Improved supervision of investigations across range of safeguarding investigations at Commands and centralised teams.

## Slide 17: Investigations cont’d…
Dec 2022 – now
Creation of Safeguarding Investigation teams in the Commands to provide.
Case study response to Online CSEA – training ongoing to ensure VOC captures all aspects of vulnerability.
Bespoke training to front line officers to be delivered around Online CSEA.
Work ongoing to improve further the investigation templates with safeguarding embedded at every review – July 2023
Templates embedded with the service directory app option so that early intervention and support can be achieved at the earliest opportunity

## Slide 18: Rec 7: Improve CSE understanding
Pre Dec 22
Multi-Agency Child Exploitation structures were reviewed and improved with partners.
Enhanced focus on child victim experiences.
Specialist teams on Command focus on perpetrators. Greater focus on child sexual exploitation required over child criminal exploitation.
New training delivered to response officers on Exploitation.

## Slide 19: Rec 7: Improve CSE understanding
Dec 22 - now
Training planned in May 2023 for Critical Incident Inspectors and Force Incident Managers.
Refreshed CSE operational problem profile has been produced. Work on Online CSEA operational problem profile.
Uplift of 6 PC approved into centralised Child Exploitation team.

## Slide 20: Rec 8: Improve use of police protection powers
Pre-Dec 22
Sect 46 Police Protection Powers workshops run for Sergeants and Inspectors.
New escalation policy created with partners.
Scrutiny panel developed with attendance from Children’s Social Care, Head of Partnership Hub and Vulnerability Assessment Team D/Inspector.
New template in development to address recording consistency issues.

## Slide 21: Police powers continued
Dec 22 –Now
Bitesize learning to develop a package around S46 police protection powers for frontline officers to access –July 2023
Current training on Neglect for frontline response officers covers a scenario whereby S46 powers are discussed as an option during a case study on the day – May 2023 to August 2023.
New template awaiting launch that will address areas raised in report.

## Slide 22: Rec 9: Improve management of registered sex offenders
Pre-Dec 22
Action plan created.
Dec - now
Performance management of Senior Leader
All staff are VISOR trained
Intensive scrutiny of processes and adherence to Authorised Professional Practice
Quality assurance work ongoing to ensure compliance against improvement plan

## Slide 23: Management of sex offenders cont’d
Bespoke PPN pro forma (referral form) introduced to enhance quality of referrals to social care
Monitoring of every PPN completed for quality assurance and 1-1 feedback for the officer for any practice identified using RAG ratings – ongoing
Peer review to undertaken by Humberside Police in May 23.

## Slide 24: Rec 10: Review of detention of children
Pre-Dec
Every child who enters custody has their full process and stay reviewed
Youth Commission assisted in developing a bespoke AWARE guide for custody staff
Children’s Society and Child Protection Inspection Officer delivered VOC Custody
Dec – now
Custody Inspection has been remitted to Criminal Justice to be included as part of custody review.

## Slide 25: Questions?